## Cutover Plan
Item # | Task | Primary | Secondary | Pre / Post Go Live | Dependency | Duration in hours | Start Date | Start Time | End Date | End Time | Status | Comments
1 | Source systems included in the current wave are [Systems Included:Pricing-SEQUENTUM TO ZONE4] | Build Team |  | Pre |  |  | 2022-10-24 |  | 2022-11-04
2 | Ensure all the tables related the source systems mentioned in the release plan are available in Zone3. Data and the related jobs are scheduled. | Build Team |  | Pre |  |  | 2022-10-24 |  | 2022-11-04
3 | IT Ticket Creation | Jeff / Sheetal |  | Pre |  | 2 | 2022-10-24 |  | 2022-11-04 |  | In Progress | Tickets: DFCT0024021
4 | UAT Sign off | Frank |  | Pre |  |  | 2022-10-24 |  | 2022-11-04 |  | In Progress
5 | CAB Approval | Jeff |  | Pre |  |  | 2022-10-24 |  | 2022-11-04 |  | Not Started
6 | Cutover Plan, Runbook(One) | Ambika/Bala | Bala | Pre |  |  | 2022-10-24 |  | 2022-11-04 |  | In Progress
7 | BRD, Architecture, HOTS transition steps | Ambika/Bala | Bala | Pre |  | 5 | 2022-10-24 | 9:30am EST | 2022-11-04 | 10:30am EST | In Progress
8 | Prepare DBT scripts for all DDL objects | Ambika/Bala |  | Pre |  |  | 2022-10-24 |  | 2022-11-04 |  | In Progress
9 | Prepare Release plan | Ambika/Bala |  | Pre |  |  | 2022-10-24 |  | 2022-11-04 |  | In Progress
10 | Implement release plan | Caspian Run Team |  | Pre |  |  | 2022-11-04 |  | 2022-11-04 |  | Not Started
11 | Prepare batch release plan | Caspian Run Team |  | Go-Live |  |  | 2022-11-04 |  | 2022-11-04 |  | Not Started
12 | Merge Bitbucket Feature branch to master (production) branch Repo Name: sbd-edw-main Feature Branch: feature/pricing-source-changes Pull Request: https://bitbucket.org/sbddatalake/sbd-edw-main/pull-requests/160 Repo Name: sbd-edw-pricing Feature Branch: feature/prowl-stackline-sequentum-onboarding-pricing-fixes Pull Request: https://bitbucket.org/sbddatalake/sbd-edw-pricing/pull-requests/362 | Caspian Run Team |  | Pre |  |  | 2022-11-04 |  | 2022-11-04 |  | Not Started
13 | Create Talend Adhoc Tasks in Production (One Time Load) EDW_PRC_SEQUENTUM | Caspian Run Team |  | Pre |  | 1 | 2022-11-04 |  | 2022-11-04 |  | Not Started
14 | TMC Parameters which needs to be changed in PROD during deployment : Caspian Environment – PROD Repo Branch – main | Caspian Run Team |  | Pre |  | 2 | 2022-11-04 | 9:30am EST | 2022-11-04 | 10:30am EST | Not Started | estimated time; if shorter duration then continue immediately to the next task
15 | Run the first loads | Build Team/RUN Team |  | Pre |  | 1 | 2022-11-04 |  | 2022-11-04 |  | Not Started
16 | Validate Zone 4 Source Production Migration is complete | Sheetal |  | Partial Go Live | 22,23 | 24 | 2022-11-04 |  | 2022-11-04 |  | Not Started
17 | Monitor the system after initial load | Build Team/RUN Team |  | Partial Go Live | 26 | 24 | 2022-11-04 |  | 2022-11-04 |  | Not Started
18 | Data count validation between Source (PROD_RAW) and Target (PROD_EDW) | Ambika/Bala |  | Partial Go Live | 26 | 75 | 2022-11-04 |  | 2022-11-04 |  | Not Started
19 | In case of data mismatch between source and target, check with Caspian Run Team | Caspian Run Team ¦ Build Team |  | Partial Go Live | 26 | 4 | 2022-11-04 | 11:30am EST | 2022-11-04 | 12:30pm EST | Not Started
20 | Send email to project team (All Users ) for successful / unsuccessful deployment | Caspian Run Team ¦ Build Team |  | Post Partial Go Live | 26 | 2 | 2022-11-04 | 11:30am EST | 2022-11-04 | 12:30pm EST | Not Started