## Cutover Plan
Item # | Task | Primary | Secondary | Pre / Post Go Live | Dependency | Duration in hours | Start Date | Start Time | End Date | End Time | Status | Comments
1 | Source systems included in the current wave are [Systems Included:Pricing-External Systems] [ZONE3 TO ZONE4] | Build Team |  | Pre |  |  | 2022-09-12 |  | 2022-09-12
2 | Ensure all the tables related the source systems mentioned in the release plan are available in Zone3. Data and the related jobs are scheduled. | Build Team |  | Pre |  |  | 2022-09-12 |  | 2022-09-12
3 | IT Ticket Creation | Sambhav |  | Pre |  | 2 | 2022-09-16 |  | 2022-09-16 |  | Completed | Tickets: CHG0119808 RLSE0026855 ENHC0053907
4 | UAT Sign off |  |  | Pre |  |  | 2022-09-16 |  | 2022-09-16 |  | Completed
5 | CAB Approval | SDB |  | Pre |  |  | 2022-09-22 |  | 2022-09-22 |  | In Progress
6 | Create Prod CredVaultKey/AWS secrets for Snowflake PROD_EDW database service account | Annelise |  | Pre |  | 2 | 2022-09-19 |  | 2022-09-19 |  | In Progress
7 | Confirm Bitbucket update access for Caspian Run Team | Annelise | Annelise | Pre |  | 1 | 2022-09-19 |  | 2022-09-19 |  | In Progress
8 | KT Session with Run Team | Sambhav | Sudheer | Pre |  | 20 |  |  |  |  | In Progress
9 | Cutover Plan, Runbook(One) | Sambhav | Sudheer | Pre |  |  | 2022-09-19 |  | 2022-09-19 |  | In Progress
10 | BRD, Architecture, HOTS transition steps | Sambhav | Sudheer | Pre |  | 5 | 2022-09-19 | 9:30am EST | 2022-09-19 | 10:30am EST | In Progress
11 | Prepare DBT scripts for all DDL objects | Samiuddin Ahmed Moham |  | Pre |  |  | 2022-09-19 |  | 2022-09-19 |  | In Progress
12 | Prepare Release plan | Sambhav/Samiuddin Ahmed Moham |  | Pre |  |  | 2022-09-19 |  | 2022-09-19 |  | In Progress
13 | Request for access to TMC prod (Read only) | Sruthi/Neelima/Samiuddin Ahmed Moham |  | Pre |  |  | 2022-09-19 |  | 2022-09-19 |  | In Progress
14 | Implement release plan | Caspian Run Team |  | Go-Live | 12 |  | 2022-09-23 |  | 2022-09-23 |  | In Progress
15 | Prepare batch release plan | Sambhav/Samiuddin Ahmed Moham |  | Pre |  |  | 2022-09-19 |  | 2022-09-19 |  | In Progress
16 | Repoint dbt Source pointers (Dev, Test) to PROD_RAW ( Validation step ) | Build Team | Nilanjan | Pre |  |  | 2022-09-23 |  | 2022-09-23 |  | In Progress
17 | Repoint master branch dbt Target pointers to PROD_EDW (TMC job) | Build Team | Neelima | Pre |  |  | 2022-09-19 |  | 2022-09-19 |  | In Progress
18 | Request/Check update access to the Bitbucket | Neelima/Samiuddin |  | Pre |  |  | 2022-09-19 |  | 2022-09-19 |  | In Progress
19 | Merge Bitbucket Dev branch to master (production) branch (Note: DEV here is the TEST branch) | Build team leads |  | Pre |  | 1 | 2022-09-23 |  | 2022-09-23 |  | In Progress
20 | Create Talend Adhoc Tasks in Production (One Time Load) EDW_ADHOC_METADATA EDW_OTC_RELEASE_PROD EDW_ADHOC_DYNAMICVIEW | Caspian Run Team |  | Pre |  | 2 | 2022-09-19 | 9:30am EST | 2022-09-19 | 10:30am EST | In Progress | estimated time; if shorter duration then continue immediately to the next task
21 | TMC Parameters which needs to be changed in PROD during deployment : Caspian SNOWFLAKE CredVaultKey - sbd/caspian/prod/operations/db/sbd_caspian_snowflake_edw Caspian Environment – PROD Repo Branch – main | Caspian Run Team |  | Pre |  | 1 | 2022-09-19 |  | 2022-09-19 |  | In Progress
22 | Create Talend Task (full refresh): 1. EDW_PRC_BAROMETER 2. EDW_PRC_PRICEFX 3. EDW_PRC_DATAMIND 4. EDW_PRC_WEBPRICE 5. EDW_PRC_SSACOMPETITIVEINTELLIGENCE 6. EDW_PRC_SFTPGTSI 7. EDW_PRC_USPOS | Caspian Run Team |  | Pre |  | 1 | 2022-09-12 |  | 2022-09-12 |  | In Progress | 07:30 (UTC -04:00) New York
24 | Create all Talend tasks in production with all 3 notifications as True(Slack/Jira/Email) | Caspian Run Team |  | Pre |  | 3 | 2022-09-12 |  | 2022-09-12 |  | In Progress
25 | Ensure all Autosys jobs are properly set-up and scheduled. | Pablo, Ravi, Build team |  | Pre |  | 1 | 2022-09-23 |  | 2022-09-23 |  | In Progress
26 | Run the first loads | Build Team/RUN Team |  | Partial Go Live | 22,23 | 24 | 2022-09-23 |  | 2022-09-23 |  | In Progress
27 | Validate Zone 4 Source Production Migration is complete | Ashish / Sandeep | Pablo | Partial Go Live | 26 | 24 | 2022-09-23 |  | 2022-09-23 |  | In Progress
28 | Monitor the system after initial load | Build Team/RUN Team |  | Partial Go Live | 26 | 75 | 2022-09-23 |  | 2022-09-23 |  | In Progress
29 | Data count validation between Source (PROD_RAW) and Target (PROD_EDW) | Mithil ¦ Build Team | Lokesh | Partial Go Live | 26 | 4 | 2022-09-23 | 11:30am EST | 2022-09-23 | 12:30pm EST | In Progress
30 | In case of data mismatch between source and target, check with Caspian Run Team | Caspian Run Team ¦ Build Team | Mithil / Lokesh | Post Partial Go Live | 26 | 2 | 2022-09-23 | 11:30am EST | 2022-09-23 | 12:30pm EST | In Progress
31 | Send email to project team (All Users ) for successful / unsuccessful deployment |  | Rob W | Post Partial Go Live | 26 | 1 | 2022-09-23 | 12:30pm EST | 2022-09-23 | 12:30pm EST | In Progress